## Sheet1
Task | Estimation | Actual
Create commands to add data from CSV to DB | 2 Hrs | 2.5 Hrs
Create migrations for creating required tables | 1 Hrs | 0.5 Hrs
Create API for operations | 5 Hrs | 7 Hrs